## FILTERS & MEMBRANE
OIL & GAS DEVELOPMENT COMPANY LIMITED
SINJHORO GAS FIELD - ATA 2018-19 (MECHANICAL SCOPE OF WORK - FILTERS, MEMBRANE & MISCELLANOUS JOBS)
Act # | Tag #. | Job Description | Specifications | Tools Required
Pre-shutdown Activities
1 |  | Connection for N2 Pumper
2 |  | Depressurizing and N2 purging
3 |  | Blinding of battery limits
4 |  | Installation of scaffoldings as per each equipment job access requirement
5 |  | Arrangement of cotton gloves, emery paper, cotton rags, anti-seize molykote and WD-40 by contractor
6 |  | Removal of required insulation after plant shutdown
Post-shutdown Activities
1 |  | Deblinding of battery limits
2 |  | Leak Testing and N2 purging
3 |  | Removal of all scaffoldings
4 |  | Overall housekeeping/Area Cleaning
5 |  | Removal of all detected leakages, if any, during service test
6 |  | Restoration of insulation after start-up / normal plant operation
7 |  | Deployment of skilled manpower for plant startup jobs for 07 days
GROUP-F: FILTERS:-
WO-85 | TZ-2611 A | Condensate Filter
1 |  | Dismantling of top cover flange of filter vessel | Vertical Vessel | Spanners (striking & open): (46, 41, 36 mm, hole bar, Adjustable wrench, hammers (10 lbs), Crane Fork Lifter
2 |  | Initial inspection of filter vessel and internals | Top Entry: 14" MODCO
3 |  | Cleaning of filter housing | SIZE OF VESSEL :
4 |  | Replacement of filter elements | 14" OD x 1.093" w/t SMLS Pipe
5 |  | Final inspection | Length = 2324 mm
6 |  | Box-up of vessel | TYPE OF FILTER:
7 |  | Housekeeping of area after job completion | Particle Filter
WO-86 | TZ-2611 B | Condensate Filter
1 |  | Dismantling of top cover flange of filter vessel | Vertical Vessel | Spanners (striking & open): (46, 41, 36 mm, hole bar, Adjustable wrench, hammers (10 lbs), Crane Fork Lifter
2 |  | Initial inspection of filter vessel and internals | Top Entry: 14" MODCO
3 |  | Cleaning of filter housing | SIZE OF VESSEL :
4 |  | Replacement of filter elements | 14" OD x 1.093" w/t SMLS Pipe
5 |  | Final inspection | Length = 2324 mm
6 |  | Box-up of vessel | TYPE OF FILTER:
7 |  | Housekeeping of area after job completion | Particle Filter
WO-87 | TZ-2612 | Condensate Filter Coalescer
1 |  | Dismantling of cover flange of filter vessel | Horizontal Vessel | Adjustable wrench, hole bar, Spade, Brass Hammers (10 & 6 lbs.) special filter tool
2 |  | Initial inspection of filter vessel and internals | Head Type:Ellipsodial & Modco Closure Assembly 22"
3 |  | Cleaning of filter housing | SIZE OF VESSEL :
4 |  | Replacement of filter elements | 22" OD x 1.375" w/t SMLS Pipe
5 |  | Final inspection | Length = 2200mm
6 |  | Box-up of vessel | TYPE OF FILTER:
7 |  | Housekeeping of area after job completion | Coalescer Filter
Medium: Condensate
WO-88 | TZ-2711 | Gas Filter Separator
1 |  | Dismantling of top cover flange of filter vessel | Vertical Vessel | Adjustable wrench, hole bar, Spade, Brass Hammers (10 & 6 lbs.) special filter tool
2 |  | Initial inspection of filter vessel and internals | SIZE OF VESSEL :
3 |  | Cleaning of filter housing | Dia = 356 mm, Length = 2997 mm
4 |  | Replacement of filter elements | TYPE OF FILTER:
5 |  | Final inspection | Coalescer Filter
6 |  | Box-up of vessel | Shell Thickness: 18.61mm
7 |  | Housekeeping of area after job completion | Medium: Process gas
Connection size:8"
WO-89 | TZ-2731 | Dust Filter
1 |  | Dismantling of top cover flange of filter vessel | Horizontal Vessel | Adjustable wrench, hole bar, Spade, Brass Hammers (10 & 6 lbs.) special filter tool 65MM striking spanner and combination
2 |  | Initial inspection of filter vessel and internals | Modco Closure Assembly ,Outlet: 8"
3 |  | Cleaning of filter housing | SIZE OF VESSEL :
4 |  | Replacement of filter elements | I.D = 610 mm, Length = 1930mm,Thickness :39.29mm
5 |  | Final inspection | TYPE OF FILTER:
6 |  | Box-up of vessel | Particle Filter
7 |  | Housekeeping of area after job completion | Inlet/Outlet connection siz:8"
WO-90 | T-2001 | High Pressure Separator Filter
1 |  | Dismantling of top cover flange of filter vessel | Horizontal Vessel | Adjustable wrench, hole bar, Spade, Brass Hammers (10 & 6 lbs.) special filter tool
2 |  | Initial inspection of filter vessel and internals | SIZE OF VESSEL :
3 |  | Cleaning of filter housing | OD= 457mm , L = 3000mm
4 |  | Replacement of filter elements | TYPE OF FILTER:
5 |  | Final inspection | Coalescer Filter
6 |  | Box-up of vessel
7 |  | Housekeeping of area after job completion
WO-91 | T-2002 | Medium Pressure Separator Filter
1 |  | Erection of scaffolding | Vertical Vessel | Spanners (striking & open): (46, 32, 27 mm), Adjustable wrench, hole bar, Brass Hammers (10 & 6 lbs.) Chain Block (2.5 ton) Slings & Shackles, crane 30 ton
2 |  | Isolation of vessel / blinding, if required | Head Type:Ellipsodial (Bottom Dish)
3 |  | Dismantling of top cover flange of filter vessel | Top Flange Size: 24"X600 LBS
4 |  | Initial inspection of filter vessel and internals | SIZE OF VESSEL :
5 |  | Cleaning of filter housing | OD= 610mm,L=1845mm
6 |  | Replacement of filter elements | TYPE OF FILTER:
7 |  | Cleaning/surface preparation of gasket seating surfaces | Coalescer Filter (03 Nos.)
8 |  | Final inspection | Shell Thickness: 30mm
9 |  | Box-up of vessel | Medium: Natural gas
10 |  | Removal of scaffolding
11 |  | Housekeeping of area after job completion
WO-92 | TZ-5211 | Fuel Gas Filter Separator
1 |  | Isolation of vessel / blinding, if required | Vertical Vessel | Adjustable wrench, Brass Hammers (10 & 6 lbs.) special filter tool
2 |  | Dismantling of top cover flange of filter vessel | SIZE OF VESSEL :
3 |  | Initial inspection of filter vessel and internals | (I.Dx L) 548 mm x 2010mm S/S
4 |  | Cleaning of filter housing | Shell Thickness: 10mm
5 |  | Replacement of filter elements | TYPE OF FILTER:
6 |  | Cleaning/surface preparation of gasket seating surfaces | Dust Filter
7 |  | Final inspection | Head Type:Ellipsodial (Bottom Dish)
8 |  | Box-up of vessel | Inlet/Outlet connection size: 4"x 150 LBS
9 |  | Housekeeping of area after job completion
WO-93 | TZ-6031 A | Hot Oil Duplex Filter
1 |  | Isolation of vessel / blinding, if required | Vertical Vessel | Spanners (striking & open): (32, 27 mm), Adjustable wrench, Brass Hammers (10 & 6 lbs.)
2 |  | Dismantling of top cover flange of filter vessel | SIZE OF VESSEL :
3 |  | Initial inspection of filter vessel and internals | Length = 2324 mm
4 |  | Cleaning of filter housing | TYPE OF FILTER:
5 |  | Replacement of filter elements | wire mesh strainer
6 |  | Cleaning/surface preparation of O-Ring | Filter size:
7 |  | Final inspection | Dia= 290mm,L=750mm
8 |  | Box-up of vessel
9 |  | Housekeeping of area after job completion
WO-94 | TZ-6031B | Hot Oil Duplex Filter
1 |  | Isolation of vessel / blinding, if required | Vertical Vessel | Spanners (striking & open): (32, 27 mm), Adjustable wrench, Brass Hammers (10 & 6 lbs.)
2 |  | Dismantling of top cover flange of filter vessel | SIZE OF VESSEL :
3 |  | Initial inspection of filter vessel and internals | Length = 2324 mm
4 |  | Cleaning of filter housing | TYPE OF FILTER:
5 |  | Replacement of filter elements | wire mesh strainer
6 |  | Cleaning/surface preparation of O-Ring | Filter size:
7 |  | Final inspection | Dia= 290mm,L=750mm
8 |  | Box-up of vessel
9 |  | Housekeeping of area after job completion
GROUP-G: MEMBRANE UNIT:-
WO-95 |  | Membrane Element unit
1 |  | Isolation of vessel/Skid, if required | No of filter Elements:1240 | Spanners (striking & open): (85, 75, 41, 32, 27 mm), Adjustable wrench, hole bar, Spade, Brass Hammers (10 & 6 lbs.) Chain Block (2.5 ton) Slings & Shackles, Fork Lifter
2 |  | Dismantling of end cover flanges for filters removal
3 |  | Initial inspection of filter vessel and internals
4 |  | Inspection of the Elements and replacement if required
5 |  | Cleaning of the tubes of elements
6 |  | Dismantling of old filters & installation of new filter elements if required
7 |  | Cleaning/surface preparation of gasket seating surfaces
8 |  | Final inspection
9 |  | Box-up of vessel
10 |  | Housekeeping of area after job completion
WO-96 | FC-01 | Coalescer Filter at Membrane Skid
1 |  | Isolation of vessel / blinding, if required | Vertical Vessel | Spanners (striking & open): (115, 46, 32, 27 mm), Adjustable wrench, hole bar, Brass Hammers (10 & 6 lbs.) Chain Block (2.5 ton) Slings & Shackles, crane 30 ton
2 |  | Dismantling of top cover flange and nozzle flange of filter vessel | Head Type:Ellipsodia ( Bottom dish)
3 |  | Initial inspection of filter vessel and internals | SIZE OF VESSEL :
4 |  | Cleaning of filter housing | Dia: 1371.6mm
5 |  | Dismantling of old filters & installation of new filter elements if required | TYPE OF FILTER:
6 |  | Cleaning/surface preparation of gasket seating surfaces | Coalescer Filter (51 Nos.)
7 |  | Final inspection | Shell Thickness:41.27mm
8 |  | Replacement of new gasket as per specification | Medium: Natural gas
9 |  | Box-up of vessel
10 |  | Housekeeping of area after job completion
WO-97 | T-2901 | Particle Filter at upstream of Membrane Skid
1 |  | Erection of scaffolding | Vertical Vessel | Spanners (striking & open): (85, 46, 32, 27 mm), Adjustable wrench, hole bar, Brass Hammers (10 & 6 lbs.) Chain Block (2.5 ton) Slings & Shackles, crane 30 ton
2 |  | Dismantling of top cover flange and nozzle flange of filter vessel | Head Type:Flate ( Bottom dish)
3 |  | Initial inspection of filter vessel and internals | SIZE OF VESSEL :
4 |  | Cleaning of filter housing | (I.Dx L) 548 mm x 2250 mm S/S
5 |  | Dismantling of old filters & installation of new filter elements if required | TYPE OF FILTER:
6 |  | Cleaning/surface preparation of gasket seating surfaces | Particle Filter
7 |  | Final inspection | Shell Thickness:30mm
8 |  | Box-up of vessel | Medium: Natural gas
10 |  | Removal of scaffolding
11 |  | Housekeeping of area after job completion
GROUP-B: MISCELLANEOUS JOBS:-
Act # | Tag #. | Job Description | Tools Required
WO-18 |  | Rectification of passing problem at HP filter discharge valve (4” x 900 Lbs.) Combination spanner of 30,32mm, Striking spanner of 30,32mm
WO-19 |  | Cleaning of suction strainer (03 Nos.) of Feed Gas Compressors. 36,41mm, Combination spanner, Hole bar, Crow bar, Adjustable spanner.
WO-20 |  | Rectification of HP Separators level troll’s assembly valves and drain valves 46mm, combination spanner, Hole bar, chain block-3 ton
WO-21 |  | Rectification of MP Separators level troll’s assembly valves and drain valves 41mm, combination spanner, Hole bar, chain block-3 ton
WO-22 |  | Rectification of LP Separators level troll’s assembly valves and drain valves 32mm combination spanner, Hole bar, chain block-3 ton
WO-23 |  | Rectification of Test Separators level troll’s assembly valves and drain valves 46mm combination spanner, Hole bar, chain block-3 ton
WO-24 |  | Replacement of MP header valve 4’’ x 900 Lbs. to Test Separator 36mm combination spanner with striking.
WO-25 |  | Rectification of platform of LP Separator Sling, Crane, 30,32mm combination spanners and adjustable.
WO-26 |  | Replacement of 8" isolation valves of PCV installed at LP Separator gas line 46mm combination spanner, striking, crow bar, hole bar.
WO-27 |  | Rectification of valves of Jhakro gas injection to LP and MP header 46,41mm combination spanner, chain block, crane, hole bar.
WO-28 |  | Installation of insulation at Jhakro flare line Sheets, screw driver, pliers, nose plier.
WO-29 |  | Replacement of Jhakro flare valve (2" x 1500 lbs.) 32,36mm combination, striking spanners hole, crow bar polishing papers
WO-30 |  | Replacement of 2” ball valve at nitrogen package with globe valve along with new installation of NRV 24,27mm combination spanners, crow bar, hole bar.
WO-31 |  | Rectification of seat passing problem at 8” valve at upstream of Gas Filter Separator 36,32mm striking, combination, crow bar, hole bar.
WO-32 |  | Replacement of suction valve of K-2601 Stabilizer Overhead Compressor adjustable, 12, 14mm combination spanners.
WO-33 |  | Replacement of NRV at Regeneration Gas Compressor EZ-2721 41,36mm combination spanner, striking, hole bar, crow bar
WO-34 |  | Welding of louvers lockers of Regeneration Gas Cooler EM-2711 32,36mm combination spanner, striking spanners, hole bar, crow bar
WO-35 |  | Inspection of inlet screens of Turbo-Expander & Re-compressor K-2801 32,36mm combination spanner, crow bar, striking, crow bar
WO-36 |  | Cleaning of suction strainer of Pump GZ-3041 A/B 32,36mm combination spanner, crow bar, striking spanner, crane
WO-37 |  | Servicing of fuel gas actuators of hot oil heater A 32,36mm combination spanner, crow bar, striking spanner, crane
WO-38 |  | Servicing of fuel gas actuators of hot oil heater B 32,36mm combination spanner, crow bar, striking spanner, crane
WO-39 |  | Cleaning of Turbo-expander Oil Cooler Fan, adjustable
WO-40 |  | Cleaning of level glass of C-6211 Flare Knockout Vessel 24,27,22 combination spanner, brush, jetting machine
WO-41 |  | Inspection of inlet strainer at De-Ethanizer Compressor K-3001 32,30mm combination spanner, striking spanner, crow bar
WO-42 |  | Cleaning of suction strainer of Hot Oil Pump A 36,32mm combination spanners, striking spanners, crow bar, hole bar
WO-43 |  | Cleaning of suction strainer of Hot Oil Pump B 36,32mm combination spanners, striking spanners, crow bar, hole bar
WO-44 |  | Cleaning of suction strainer of Hot Oil Pump C 36,32mm combination spanners, striking spanners, crow bar, hole bar
WO-45 |  | Cleaning of suction strainer LPG Loading Pump A 36,32mm combination spanners, striking spanners, crow bar, hole bar
WO-46 |  | Cleaning of suction strainer LPG Loading Pump B 36,32mm combination spanners, striking spanners, crow bar, hole bar
WO-47 |  | Cleaning of suction strainer LPG Loading Pump C 36,32mm combination spanners, striking spanners, crow bar, hole bar
WO-48 |  | Cleaning of suction strainer of Fire Water Pump A 36,32mm combination spanner, striking, crow bar, hole bar, wire brushes
WO-49 |  | Cleaning of suction strainer of Fire Water Pump B 36,32mm combination spanner, striking, crow bar, hole bar, wire brushes
WO-50 |  | Cleaning of oil cooler of Instrument Air Compressor A Pipe wrench 18 inches, adjustable 12mm, socket set, filter spanner
WO-51 |  | Cleaning of oil cooler of Instrument Air Compressor B Pipe wrench 18 inches, adjustable 12mm, socket set, filter spanner
WO-52 |  | Cleaning of suction strainer of Sale Gas Compressor V-2910 36,41mm combination spanner, crow bar, hole bar
WO-53 |  | Cleaning of suction strainer of Sale Gas Compressor V-2911 36,41mm combination spanner, crow bar, hole bar
WO-54 |  | Cleaning of suction strainer of Sale Gas Compressor V-2912 36,41mm combination spanner, crow bar, hole bar
WO-55 |  | Rectification of seat passing problem of drain valve (2") of Particle Filter Hack saw or Grinder 9"
WO-56 |  | Replacement of NRV (1”) at seal gas system of Turbo Expander 22,20mm combination spanner, adjustable
WO-57 |  | Replacement of valve (3”) at fuel gas skid 27,30mm combination, striking spanner, crow bar
WO-58 |  | Installation of cold insulation at Feed Gas Compressors recycle line Screw driver, Cutter, Scissor
WO-59 |  | Installation of cold insulation of remaining pipe in LPG Area and Jakhro Separator Screw driver, Cutter, Scissor
WO-60 |  | Installation of cold insulation of remaining pipe at Jakhro Separator Screw driver, Cutter, Scissor
WO-61 |  | Installation of cold insulation of remaining pipe in LPG Area Screw driver, Cutter, Scissor
WO-62 |  | Installation of cold insulation at Well Jakhro Flare Line Screw driver, Cutter, Scissor
WO-63 |  | Inspection of Louvers of Feed Gas Compressor V-2001 and repair, if required 22,20mm combination spanner, adjustable, Screw driver, crow bar
WO-64 |  | Inspection of Louvers of Feed Gas Compressor V-2002 and repair, if required 22,20mm combination spanner, adjustable, Screw driver, crow bar
WO-65 |  | Inspection of Louvers of Feed Gas Compressor V-2003 and repair, if required 22,20mm combination spanner, adjustable, Screw driver, crow bar
WO-66 |  | Inspection of Louvers of Sale Gas Compressor V-2910 and repair, if required 22,20mm combination spanner, adjustable, Screw driver, crow bar
WO-67 |  | Inspection of Louvers of Sale Gas Compressor V-2911 and repair, if required 22,20mm combination spanner, adjustable, Screw driver, crow bar
WO-68 |  | Inspection of Louvers of Sale Gas Compressor V-2912 and repair, if required 22,20mm combination spanner, adjustable, Screw driver, crow bar
WO-69 |  | Replacement of Jhakro Flare Valve (2" x 1500 Lbs.) 22,20mm combination spanner, adjustable
WO-70 |  | Installation of HD # 01 LP Header Valve 6" x 900 lbs. 22,20mm combination spanner, adjustable
WO-71 |  | Installation of Test Separator Outlet Valve to Flare 4" x 900 Lbs. 22,20mm combination spanner, adjustable
WO-72 |  | Replacement of Regeneration Scrubber downstream valve 3" x 900 lbs. 22,20mm combination spanner, adjustable
WO-73 |  | Replacement of 8" x 600 lbs. RF Ball Valve with Globe Valve at LPG area bypass line 22,20mm combination spanner, adjustable
WO-74 |  | Rectification of drain valve 1" at De-Butanizer Reboiler 22,20mm combination spanner, adjustable
WO-75 |  | Rectification of De-Ethanizer Reboiler level glass isolating valve 1" 22,20mm combination spanner, adjustable

## Sheet1 (hidden)
Equipment | Qty
Columns | 2
Vessels
Exchangers
Pumps
Incinerator

## ManPower (hidden)
Manpower For ATA-Uch-II
Sr.No. | Craft | Qty | Days
Columns
1 | Fitter | 8 | 7
2 | Helper | 4 | 7
Total |  | 12 | 14
Vessels
1 | Scaffolder | 59 | 7
2 | Fitter | 66 | 7
3 | Helper | 39 | 7
|  | 164 | 21
Heat Exchanger
1 | Scaffolder | 16 | 7
2 | Fitter | 17 | 7
3 | Rigger | 8 | 7
4 | Helper | 11 | 7
Total |  | 52 | 28
Rotary
1 | Millwright | 8 | 7
2 | Fitter | 4 | 7
3 | Helper | 2 | 7
Total |  | 14 | 21
Incinerator
1 | Fitter | 4 | 7
Total |  | 4 | 7
Additional Manpower
1 | Fitter | 20 | 7
2 | Helper | 10 | 7
3 | Scafloder | 6 | 7
4 | Rigger | 6 | 7
5 | Welder | 2 | 7
6 | Fabricator | 2 | 7
7 | Insulator | 2 | 7
Total |  | 48 | 49
G.Total |  | 294 | 140
Equipment
Sr.No. | Equipment | Qty | Days
1 | Crane (50T) | 1 | 7
2 | Jetting M/c | 1 | 7