## COLUMNS & MISC JOBS
OIL & GAS DEVELOPMENT COMPANY LIMITED
UCH-II GAS PROCESSING PLANT - ATA 2018
(MECHANICAL SCOPE OF WORK - COLUMNS & MISC. JOBS)
Act # | Tag #. | Job Description | Specifications | Tools Required | Remarks
Pre-shutdown Activities
1 |  | Connection for N2 Pumper
2 |  | Depressurizing and N2 purging
3 |  | Blinding of battery limits
4 |  | Installation of scaffoldings as per each equipment job access requirement
Post-shutdown Activities
1 |  | Deblinding of battery limits
2 |  | Leak Testing and N2 purging
3 |  | Removal of all scaffoldings
4 |  | Overall housekeeping/Area Cleaning
5 |  | Skilled manpower will be deployed for startup activities for 07 days after shutdown.
GROUP-A: COLUMNS:-
MA1 | 300-T-101 | Amine Contactor (02 Nos)
1 | & | Blinding | Height of Contactor : 43 ft | Strik.Spanner: 70,75,60mm | Arrangement for chem.
2 | 310-T-101 | Provision of connections for chem. cleaning/water flushing | I.D. of Contactor : 122 in. | Comb.Sp.16,17mm (Trays) | circulation & water flush-
3 |  | Opening of manways (02 Nos.) | No. of trays : 12 nos. | Socket Set, | ing is available at site.
4 |  | Ventilation / Safety clearance | Size of Manway : 24 in.x 600 CL | Adjustable Spanner
5 |  | Initial inspection
6 |  | Internal complete mech. cleaning of trays, demisters, vessel, LG's etc.
7 |  | Final Inspection
8 |  | Boxup
9 |  | Deblinding
MA2 | 300-T-102 | Amine Regenerator (2 Nos)
1 | & | Blinding | Height of Stripper : 60 ft | Strik.Spanner: 50,41 mm | Arrangement for chem.
2 | 310-T-102 | Provision of connections for chem. cleaning/water flushing | I.D. of Stripper : 10.5 in. | Comb.Sp.16,17mm (Trays) | circulation & water flush-
3 |  | Opening of manways (03 Nos.) | No's. of trays : 23 nos. | Socket Set, | ing is available at site.
4 |  | Ventilation / Safety clearance | Size of Manway : 24 in.x 150 CL | Adjustable Spanner
5 |  | Initial inspection
6 |  | Internal complete mech. cleaning of trays, demisters, vessel, LG's etc.
7 |  | Final Inspection
8 |  | Boxup
9 |  | Deblinding
MA3 | 400-T-101 | Glycol Contactor (02 Nos)
1 | & | Blinding | Height of Contactor : 52 ft | Str.Spanner: 46,50 mm
2 | 410-T-101 | Opening of manways (02 Nos) | I.D. of Contactor : 90 in. | Open/Ring Sp: 20,22,24,27mm
3 |  | Ventilation / Safety clearance | No. of trays : 12 nos.
4 |  | Initial inspection | Size of Manway : 24 in.x 600 CL
5 |  | Internal cleaning of packing, demisters, vessel, LG's etc.
6 |  | Final Inspection
7 |  | Boxup
8 |  | Deblinding
GROUP-B: MISCELLANEOUS JOBS:-
MB1 | Dehydration Train-1 & 2 | Installation of Isolating Valves (2" x 600CL, Ball Valve, Flanged - 04 Nos.) at Level Briddle of Glycol Contractors
MB2 | Amine Train-2 | Onsite Inspection and Servicing of Reboiler-A Hot Oil supply FCV upstream isolating valve 16"-300 CL (01 No.)
MB3 | Amine Train-2 | Alignment Flange & replacement of Expansion Joint 14"x150CL at Inlet (rich Amine) of X-Heat Exchanger

## Sheet1 (hidden)
Equipment | Qty
Columns | 2
Vessels
Exchangers
Pumps
Incinerator

## ManPower (hidden)
Manpower For ATA-Uch-II
Sr.No. | Craft | Qty | Days
Columns
1 | Fitter | 8 | 7
2 | Helper | 4 | 7
Total |  | 12 | 14
Vessels
1 | Scaffolder | 59 | 7
2 | Fitter | 66 | 7
3 | Helper | 39 | 7
|  | 164 | 21
Heat Exchanger
1 | Scaffolder | 16 | 7
2 | Fitter | 17 | 7
3 | Rigger | 8 | 7
4 | Helper | 11 | 7
Total |  | 52 | 28
Rotary
1 | Millwright | 8 | 7
2 | Fitter | 4 | 7
3 | Helper | 2 | 7
Total |  | 14 | 21
Incinerator
1 | Fitter | 4 | 7
Total |  | 4 | 7
Additional Manpower
1 | Fitter | 20 | 7
2 | Helper | 10 | 7
3 | Scafloder | 6 | 7
4 | Rigger | 6 | 7
5 | Welder | 2 | 7
6 | Fabricator | 2 | 7
7 | Insulator | 2 | 7
Total |  | 48 | 49
G.Total |  | 294 | 140
Equipment
Sr.No. | Equipment | Qty | Days
1 | Crane (50T) | 1 | 7
2 | Jetting M/c | 1 | 7