## UTILITIES & MOD JOBS
OIL & GAS DEVELOPMENT COMPANY LIMITED
UCH-II GAS PROCESSING PLANT - ATA 2018 (MECHANICAL SCOPE OF WORK - UTILITIES & MODIFICATION JOBS)
Act # | Tag #. | Job Description | Specifications | Tools Required | Remarks
Pre-shutdown Activities
1 |  | Connection for N2 Pumper
2 |  | Depressurizing and N2 purging
3 |  | Blinding of battery limits
4 |  | Installation of scaffoldings as per each equipment job access requirement
Post-shutdown Activities
1 |  | Deblinding of battery limits
2 |  | Leak Testing and N2 purging
3 |  | Removal of all scaffoldings
4 |  | Overall housekeeping/Area Cleaning
5 |  | Skilled manpower will be deployed for startup activities for 07 days after shutdown.
GROUP-D: UTILITIES
MD1 | 350-H-101 | Incinerator Unit
1 |  | Blinding | Size of Manway : 30" x 150 CL | Spanner: 32mm
2 |  | Opening of 30 " manway. | Size : I.D. 16ft, Length: 46ft
3 |  | Ventilation / Safety clearance
4 |  | Initial inspection of Combustion Chamber, Refractory, Burners & Pilots etc.
5 |  | Repairing of Refractory if required. |  |  | By OGDCL
6 |  | Final Inspection
7 |  | Boxup
8 |  | Deblinding
MD2 | 300-CT-101 | Cooling Tower
1 | & | Basin Cleaning | Type: Induced Draft Counterflow | General Tool Box
2 | 310-CT-101 | Inspection/Cleaning/Re-arrangement of Drift Eliminators | Design Water Circulation: 8769.2 US gpm
3 |  | Water distributor Inspection / Cleaning | No. of Modules: 08 No of Cells per Module: 02
4 |  | Cleaning of Air intake Panels | Basin Size(LxWxD): 144x48x4 ft.
5 |  | Cooling Water Pump 310-P-111A NRV (24"-150) stucking problem rectification | By: Ilmed I,Pianti Italy
6 |  | Final Inspection
MD3 |  | Hot Oil Fuel Gas Strainer A/B/C/D
1 |  | Strainer Inspection / Cleaning and repair if any |  | General Tool Box
2 |  | Boxup
MD4 | 900-S101-A | Hot Oil Main Strainer
1 |  | Opening of Cover |  | Strik.Span: 41, General Tool Box
Initial Inspection
Cleaning of strainer
Final Inspection
2 |  | Boxup |  | Crane-45Ton,
MD5 | 900-F101-A/B | Hot Oil Side Filters
1 |  | Strainer Inspection / Cleaning and repair if any |  | Strik.Span: 60, General Tool Box
2 |  | Boxup |  | Crane-45Ton,
MD6 | 350-V-101 | Incinerator K.O Drum
1 |  | Blinding | Vertical Vessel | Strik.Spner: 55,50mm
2 |  | Opening of manways | Size of Manway : 24" x 150 CL | Comb,Spner: 24,27,36,41mm
3 |  | Ventilation/safety clearance | Size of Vessel : 118" ID x 161" L | Scaffolding Material
4 |  | Initial Inspection | Main Material : SA-240, TP.304L
5 |  | Internal cleaning of complete vessel, LG's/LT's etc.
6 |  | Final Inspection
7 |  | Box up
8 |  | Deblinding
MD7 | 940-V-102 | Slope Vessel
1 |  | Blinding | Horizontal Vessel | Strik.Spner: 46,50mm
2 |  | Opening of manways | Size of Manway : 20" x 150 CL | Scaffolding Material
3 |  | Ventilation/safety clearance | Size of Vessel : 79 I.D. X 300" L
4 |  | Initial Inspection | Material : SA516-70/SA105
5 |  | Internal cleaning of complete vessel and its pit
6 |  | Cleaning of LG's/LT's
7 |  | Final Inspection
8 |  | Box up
9 |  | Deblinding
MD8 | 940-V-101 | Blow Case Vessel
1 |  | Blinding | Horizontal Vessel | Strik.Spner: 46,50mm
2 |  | Opening of manways | Size of Manway : 18" x 300 CL | Comb,Spner: 24,27,30,32mm
3 |  | Ventilation/safety clearance | Size of Vessel : 1220 mm ID x 3660mm L
4 |  | Initial Inspection | Main Material : SA-516-70
5 |  | Internal cleaning of complete vessel, LG's/LT's etc.
6 |  | Inspection
7 |  | Box up
8 |  | Deblinding
MD9 | 990-V-101 | Flare K.O Drum
1 |  | Blinding | Horizontal Vessel | Strik.Spanner:46mm
2 |  | Opening of manways | Size of Manway : 24" x 150 CL | Comb,Spner:24,27mm
3 |  | Ventilation/safety clearance | Size of Vessel : 118" ID x 446" L
4 |  | Initial Inspection | Material : SA-516 Gr.70
5 |  | Internal cleaning of complete vessel, LG's/LT's etc.
6 |  | Final Inspection
7 |  | Box up
8 |  | Deblinding
MD10 | 960-V-102 | Fuel Gas Knock Out
1 |  | Blinding | Vertical Vessel | Strik.Spanner:46mm
2 |  | Opening of manways | Size of Manway : 20" x 150 CL | Comb,Spner:24,27mm
3 |  | Ventilation/safety clearance | Size of Vessel : 1375mm ID x 3965mm L
4 |  | Initial Inspection | Material : SA-516 Gr.70
5 |  | Internal cleaning of complete vessel, LG's/LT's etc.
6 |  | Final Inspection
7 |  | Box up
8 |  | Deblinding
MD11 | 950-TK-102- | CPI (Oily Water Treatment System)
1 | A/B/C | Initial Inspection of all pits. | Inlet Pit, Oil Chamber, Water Pit
2 |  | Decanting / Cleaning of all pits | Size: 51360mm L x 4080mm W x 4228mm H
3 |  | Final Inspection
GROUP-E: MODIFICATION JOBS:-
ME1 | Dehydration Train-1 & 2 | Dehydration Regenerator line top vent to be syemmatrical as Uch-1 Dehy trains | 1. Removal of 6" Pipe Spools. 2. One Chamfer Cut of 6" pipe. 3. Install back 1 chamferred Spool.
ME2 | SGT-100-1/2/3 | Re-routing of SGT's Close Drain Lines | 1- Cutting/Removel Existing 1" dia. CS Line. 2- Welding/Fabrication of 1" dia CS line (20 Joints) and 1-1/2" dia. CS line (16 Joints)
ME3 | Amine Train-2 | Re-routing of Amine Train-2 Treated Gas Outlet Line as per Original Scheme | 1. Cutting of 14" dia. Pipe SS 316 Sch 40 = 3 Joints 2. Welding/Fabrication of:14" dia.pipe SS 316 Sch 40 = 3 Joints 3. Flange boxup with 12 "x600CL Valve. 4. RT of new weld joints
ME4 | 900-P-102 A/C | Replacement of Hot Oil Pump-A & C Suction Valves + Discharge NRV Bypass Valve | 1. Replacement of 12"150 Gate valves. (Flanged) 2. Replacement of 3/4"-800 Gate valve socket weld. (cutting and welding job)
ME5 | Amine Train-2 & Incinerator Area | Relocation of Various Inst Air Lines in 300/310/350 area relocation to avoid fall/slip hazarad | For 310: 1. 1/2 SS line cutting and re routing on supports. 2. Welding Joints 1/2" dia. S.S. pipe = 15 Nos (approx) For 350: 1. 1/2 G.I. line cutting and re routing. 2. Threaded Joints (Joints 1/2" = 15 Nos approx)
ME6 | Dehydration Train-1 & 2 | Installation of Isolation Valves of Glycol Flash Drum PCVs. | 1. Removal of Spool from skid. 2. Cutting of 1-1/2" SS pipe 3. Welding of 04 Nos. SS Flanges (1-1/2"-150CL) for Installation of 1-1/2" x 150CL Gate Valve (02 Nos.) 4. Boxup
ME7 |  | Removal of Existing 1-1/2" Line from Flare KO pump headers and installation of end blind | 1. Cutting of Existing Pipe 1-1/2" at header End 2. Welding of Flange 1-1/2" on Header End 3. installation of End Blind
ME8 |  | Rerouting of Lines Leading from Skid 1,2,3 towards Pipe rack: | 1. 1-1/2" line to condensate water separator (No of Weld Joints = 6) 2. 2" line to close drain (No. of Weld Joints = 6) 3. 2" line to Hot Oil Sump (No. of Weld Joints = 6) 4. 1" line from Flash Drum to Close Drain (No. of Weld Joints = 6) 5. Excavation will be required for above sr.# 2, 3, & 4.

## Sheet1 (hidden)
Equipment | Qty
Columns | 2
Vessels
Exchangers
Pumps
Incinerator

## ManPower (hidden)
Manpower For ATA-Uch-II
Sr.No. | Craft | Qty | Days
Columns
1 | Fitter | 8 | 7
2 | Helper | 4 | 7
Total |  | 12 | 14
Vessels
1 | Scaffolder | 59 | 7
2 | Fitter | 66 | 7
3 | Helper | 39 | 7
|  | 164 | 21
Heat Exchanger
1 | Scaffolder | 16 | 7
2 | Fitter | 17 | 7
3 | Rigger | 8 | 7
4 | Helper | 11 | 7
Total |  | 52 | 28
Rotary
1 | Millwright | 8 | 7
2 | Fitter | 4 | 7
3 | Helper | 2 | 7
Total |  | 14 | 21
Incinerator
1 | Fitter | 4 | 7
Total |  | 4 | 7
Additional Manpower
1 | Fitter | 20 | 7
2 | Helper | 10 | 7
3 | Scafloder | 6 | 7
4 | Rigger | 6 | 7
5 | Welder | 2 | 7
6 | Fabricator | 2 | 7
7 | Insulator | 2 | 7
Total |  | 48 | 49
G.Total |  | 294 | 140
Equipment
Sr.No. | Equipment | Qty | Days
1 | Crane (50T) | 1 | 7
2 | Jetting M/c | 1 | 7