## VESSELS
OIL & GAS DEVELOPMENT COMPANY LIMITED
UCH-II GAS PROCESSING PLANT - ATA 2018 (MECHANICAL SCOPE OF WORK - VESSELS)
Act # | Tag #. | Job Description | Specifications | Tools Required | Remarks
Pre-shutdown Activities
1 |  | Connection for N2 Pumper
2 |  | Depressurizing and N2 purging
3 |  | Blinding of battery limits
4 |  | Installation of scaffoldings as per each equipment job access requirement
Post-shutdown Activities
1 |  | Deblinding of battery limits
2 |  | Leak Testing and N2 purging
3 |  | Removal of all scaffoldings
4 |  | Overall housekeeping/Area Cleaning
5 |  | Skilled manpower will be deployed for startup activities for 07 days after shutdown.
GROUP-F: VESSELS:-
MF1 | 210-V-101 | Slug Catcher Eastern
1 |  | Blinding | Horizontal Vessel | Strik.Span:65,50,41 mm
2 |  | Opening of manway | Size of Manway : 20" x 600 CL | Comb.Span.:27,32mm
3 |  | Ventilation/Safety clearance | Size of Vessel : 83" ID x 328" L | Adjustable Spanner
4 |  | Initial Internal Inspection of vessel and demister
5 |  | Cleaning of complete vessel, Demister & LG's etc.
6 |  | Final inspection
7 |  | Boxup
8 |  | Deblinding
MF2 | 211-V-101 | Slug Catcher Central
1 |  | Blinding | Horizontal Vessel | Strik.Span:65,41 mm
2 |  | Opening of manway | Size of Manway : 20" x 600 CL | Comb.Span.:27mm
3 |  | Ventilation/Safety clearance | Size of Vessel : 83" ID x 328" L | Adjustable Spanner
4 |  | Initial Internal Inspection of vessel and demister |  | Crow Bar
5 |  | Cleaning of complete vessel, demister & LG's etc.
6 |  | Final inspection
7 |  | Boxup
8 |  | Deblinding
MF3 | 212-V-101 | Slug Catcher Western
1 |  | Blinding | Horizontal Vessel | Strik.Span:65,41 mm
2 |  | Opening of manway | Size of Manway : 20" x 600 CL | Comb.Span.:27mm
3 |  | Ventilation/Safety clearance | Size of Vessel : 94" ID x 379" L | Adjustable Spanner
4 |  | Initial Internal Inspection of vessel and demister |  | Crow Bar
5 |  | Cleaning of complete vessel, demister & LG's etc.
6 |  | Final inspection
7 |  | Boxup
8 |  | Deblinding
MF4 | 250-V-101 | Condensate Water Separator
1 |  | Blinding | Horizontal Vessel | St.Sp.: 46 mm
2 |  | Opening of manway | Size of Manway : 20" x 150 CL | Comb.Sp.: 24,27mm
3 |  | Ventilation/Safety clearance | Size of Vessel : 59" ID x 229" L | Adjustable Spanner
4 |  | Initial Internal Inspection of vessel
5 |  | Cleaning of vessel, demisters & LG's.
6 |  | Final inspection
7 |  | Boxup
8 |  | Deblinding
MF5 | 250-V-102 | Condensate Degassing Boot
1 |  | Blinding | Vertical Vessel | St.Sp.: 46 mm
2 |  | Opening of manway | Size of Manway : 18" x 150 CL | Comb.Sp.: 24,27mm
3 |  | Ventilation/Safety clearance | Size of Vessel : 1070mm ID x 3355mm L | Adjustable Spanner
4 |  | Initial Internal Inspection of vessel
5 |  | Cleaning of vessel, demisters & LG's.
6 |  | Final inspection
7 |  | Boxup
8 |  | Deblinding
MF6 | 300-V-101 | Feed Gas K.O Drum (2 Nos)
1 | & | Blinding | Vertical Vessel | Strik. Span: 70,65mm
2 | 310-V-101 | Opening of manway | Size of Manway : 24" x 600 CL | Comb;Spanner: 27,30mm
3 |  | Ventilation/safety clearance | Size of Vessel : 45.27" I.D. X 100.4" L | Scaffodling Material
4 |  | Initial Internal Inspection of vessel |  | Crow Bar, Chain Blocks
5 |  | Internal cleaning of complete vessel, LG's/LT's etc.
6 |  | Final Inspection
7 |  | Box up
8 |  | Deblinding
MF7 | 300-V-102 | Feed Gas Filter Coalescer (02 Nos)
1 | & | Opening Of Top Cover | Vertical Vessel | Strik. Span: 65mm
2 | 310-V-102 | Inspection Of Filter Coalescer Elements | Size of Vessel : 43.3" I.D. X 185.4" TL-TL | Comb;Spanner: 27,30mm
3 |  | Replacement Of Filter Coalescer Elements
4 |  | Final Inspection
5 |  | Box up
MF8 | 300-S101 A/B | Lean Amine Duplex Strainers (04 Nos)
1 | & | Opening of 28" Cover |  | Strik.Span: 32 mm
2 | 310-S101 A/B | Initial Inspection |  | Hammers, Crow bar
3 |  | Cleaning of strainer |  | Scaffolding material
4 |  | Final Inspection
5 |  | Boxup
MF9 | 300-S105 A/B | Rich Amine Duplex Strainers (04 Nos)
1 | & | Opening of 28" Cover |  | Strik.Span: 32 mm
2 | 310-S105 A/B | Initial Inspection |  | Hammers, Crow bar
3 |  | Cleaning of strainer |  | Scaffolding material
4 |  | Final Inspection
5 |  | Boxup
MF10 | 300-V-104 | Rich Amine Flash Drum (02 Nos)
1 | & | Blinding | Horizontal Vessel | Str.Spanner: 46,50 mm | Arrangement for chem.
2 | 310-V-104 | Provision of connections for chem. cleaning/water flushing | Size of Manway : 24" x 150 CL | Open/Ring Sp: 20,22,24,27mm | circulation & water flush-
3 |  | Opening of manway | Size of Vessel :137.8" I.D. X 511.8"L | Crow bar, Chain Blocks | ing is available at site.
4 |  | Ventilation/safety clearance | Material : SA-240, TP.304/304L | Scaffolding Material
5 |  | Initial Inspection of vessel
6 |  | Dismantling/removal of demisters & repair/replacement if any
7 |  | Internal cleaning of complete Vessel & LG's.
8 |  | Cleaning of demisters & re-installation
9 |  | Final Inspection
10 |  | Box up
11 |  | Deblinding
MF11 | 300-V-105 | Amine Surge Vessel (02 Nos)
1 | & | Blinding | Horizontal Vessel | Str.Spanner: 46 mm
2 | 310-V-105 | Opening of manway | Size of Manway : 24" x 150 CL | Open/Ring Sp: 20,22,24,27mm
3 |  | Ventilation/safety clearance | Size of Vessel :3550mm I.D. X 12000mm L | General Tool Box
5 |  | Initial Inspection of vessel | Material : SA-240, TP.304/304L
6 |  | Internal cleaning of complete vessel, vertex breaker, LG's etc.
7 |  | Final Inspection
8 |  | Box up
9 |  | Deblinding
MF12 | 300-V-106 | Amine Reflux Drum (02 Nos)
1 | & | Blinding | Vertical Vessel | Strik.Spner: 46 mm
2 | 310-V-106 | Opening of manway | Size of Manway : 24" x 150 CL | Comb,Spner: 24,27mm
3 |  | Ventilation/safety clearance | Size of Vessel : 1880mm ID x 3370mm L | General Tool Box
4 |  | Initial Inspection | Main Material : SA-240, TP.304L
5 |  | Internal cleaning of complete vessel, LG's/LT's etc.
6 |  | Inspection, cleaning/repair of Demisters, if any
8 |  | Final Inspection
9 |  | Box up
10 |  | Deblinding
MF13 | 300-V-107 | Amine Sump Drum (02 Nos)
1 | & | Blinding | Horizontal Vessel | Strik.Spner: 46 mm
2 | 310-V-107 | Opening of manway | Size of Manway : 24" x 150 CL | Comb,Spner: 24,27,36,41mm
3 |  | Ventilation/safety clearance | Size of Vessel : 3150mm ID x 12000 mm L | General Tool Box
4 |  | Initial Inspection | Material : SA-240, TP.304L
5 |  | Decanting of Sump Vessel
6 |  | Opening/removal of A. Sump Pump
7 |  | Inspection of Pump and rectification if any
8 |  | Internal cleaning of complete vessel, LG's/LT's etc.
9 |  | Final Inspection
10 |  | Box up
11 |  | Deblinding
MF14 | 400-V-103 | Glycol Flash Separator (02 Nos)
1 | & | Blinding | Horizontal Vessel | Strik.Spner: 50mm
2 | 410-V-103 | Opening of manway | Size of Manway : 24" x 150 CL | Comb,Spner: 24,27,36mm
3 |  | Ventilation/safety clearance | Size of Vessel : 4.43 ft ID x 12.47 ft L | General Tool Box
4 |  | Initial Inspection | Main Material : SA-240, 304/304L
5 |  | Internal cleaning of vessel, demisters, LG's etc.
6 |  | Final Inspection
7 |  | Box up
8 |  | Deblinding
MF15 | 400-V-104 | Glycol Surge Vessel (02 Nos)
1 | & | Blinding | Horizontal Vessel | Strik.Spner: 50mm
2 | 410-V-104 | Opening of manway | Size of Manway : 24" x 150 CL | Comb,Spner: 24,27,36mm
3 |  | Ventilation/safety clearance | Size of Vessel : 4.59 ft ID x 14.76 ft L | Scaffolding Material
4 |  | Initial Inspection | Main Material : ASTM A516 Gr. 70N | General Tool Box
5 |  | Internal cleaning of vessel, demisters, LG's etc.
6 |  | Final Inspection
7 |  | Box up
8 |  | Deblinding
MF16 | 400-V-105 | Glycol Sump Vessel (02 Nos)
1 | & | Blinding | Horizontal Vessel | Strik.Spner: 50mm
2 | 410-V-105 | Opening of manways | Size of Manway : 24" x 150 CL | Comb,Spner: 24,27,36mm
3 |  | Ventilation/safety clearance | Size of Vessel : 6.24 ft ID x 19.68 ft L | Scaffolding Material
4 |  | Initial Inspection | Main Material : ASTM A516 Gr. 70N | General Tool Box
5 |  | Internal cleaning of vessel, demisters, LG's etc.
6 |  | Final Inspection
7 |  | Box up
8 |  | Deblinding

## Sheet1 (hidden)
Equipment | Qty
Columns | 2
Vessels
Exchangers
Pumps
Incinerator

## ManPower (hidden)
Manpower For ATA-Uch-II
Sr.No. | Craft | Qty | Days
Columns
1 | Fitter | 8 | 7
2 | Helper | 4 | 7
Total |  | 12 | 14
Vessels
1 | Scaffolder | 59 | 7
2 | Fitter | 66 | 7
3 | Helper | 39 | 7
|  | 164 | 21
Heat Exchanger
1 | Scaffolder | 16 | 7
2 | Fitter | 17 | 7
3 | Rigger | 8 | 7
4 | Helper | 11 | 7
Total |  | 52 | 28
Rotary
1 | Millwright | 8 | 7
2 | Fitter | 4 | 7
3 | Helper | 2 | 7
Total |  | 14 | 21
Incinerator
1 | Fitter | 4 | 7
Total |  | 4 | 7
Additional Manpower
1 | Fitter | 20 | 7
2 | Helper | 10 | 7
3 | Scafloder | 6 | 7
4 | Rigger | 6 | 7
5 | Welder | 2 | 7
6 | Fabricator | 2 | 7
7 | Insulator | 2 | 7
Total |  | 48 | 49
G.Total |  | 294 | 140
Equipment
Sr.No. | Equipment | Qty | Days
1 | Crane (50T) | 1 | 7
2 | Jetting M/c | 1 | 7